## Slide 1: Plan Elaboration And Project Identification, and Formulation
Dr. Tahir Nadeem

## Slide 2: Concept
Elaboration is the process of adding more information to existing, relatively simple information to create a more complex, emergent whole. Elaboration may involve planning or executing a task with painstaking attention to numerous parts or details.

## Slide 3: Plan Elaboration
Plan normally is a brief document. For implementation many more details are required.
Moreover plan gives us a big picture of future development, which needs to be cut down into small pieces. That process of division helps in execution, supervision and evaluation of plan.

## Slide 4: Steps in Plan Elaboration
Programming
Project Identification
Regionalization

## Slide 5: Process of Plan Elaboration
Programing
Program 1
Program 2
Project Identification
Project 1
Project 2
Regionalization
District 1
District 2

## Slide 6
Secondary Education Sector
Science education improvement
Construction of schools
Science education improvement
Construction of labs
Revision of science books
Construction of labs
1 lab in Dera bakha School
1 Lab in Tamewali School

## Slide 7: What is a Project?
A project is a sequence of unique, complex, and connected activities having one goal or purpose and that must be completed by a specific time, within budget, and according to specifications.

## Slide 8: Project basis (SWOT Analysis)

## Slide 9: Project Formulation
What has to be done, why and How?

## Slide 10: What has to be done and why?
Details of the project (WBS)

## Slide 11: Identifying the goal, objectives, and target group
Background of the project Defined goal and objectives The societal vision of the organization Expected short-term and long-term results Beneficiaries of the project Problems solved by the project
ACTIVITY: Establish a Computer Lab
(Draw Objectives)

## Slide 12: Contents
Theme and main issues to be covered
Methods chosen to realize the goal and objectives
Activities to be implemented
Further needs to continue the project
ACTIVITY: Write down the contents of the above project

## Slide 13: And How?
Plan of Operations (planops)
ACTS
Agency
Time
Space
Cost

## Slide 14: Project location's and time schedule of activities
Location of different activities
Duration of the project
Starting and ending dates of the project
Schedule for individual activities
Summarized timeline of the project
ACTIVITY: Write down the time schedule of the above project

## Slide 15: Resources
Human resources
Financial resources
Infrastructure
  Men
  Money
  Material
  Machinery
  Management
ACTIVITY: Calculate the resources required for the above project

## Slide 16: Description of the implementing organization and partners
Description of the implementing organization
Analysis of capacity and capability
Description of cooperative partners
Analysis of partners capacity and capability
ACTIVITY: give details of management staff

## Slide 17: Monitoring, Evaluation and follow-up
Success criteria of the project
Method and timing of monitoring and evaluation
Further plans and follow up
ACTIVITY: Identify performance indicators

## Slide 18: Preparing an Activity Plan
Activity Breakup into Tasks
Clarify sequence & dependence
Timeline for each task
Using milestones
Define expertise
Allocate tasks among the team

## Slide 19: Planning Commission’s Performa
PC I Formulation of projects
PC II Feasibility study
PC III Quarterly monitoring
PC IV Completion report
PC V Annual Assessment report

## Slide 20: PC-1 FORM (SOCIAL SECTORS)
1 | Name of the Project
2 | Location
3 | Authority responsible for:
i. | Sponsoring
ii. | Execution
iii. | Operation and maintenance
iv. | Concerned federal ministry
4 | Plan Provision
5 | Project objectives and its relationship with Sect-oral objectives
6 | Description, justification and technical parameters

## Slide 21
7 | Capital cost estimates
8 | Annual operating and maintenance cost after completion of the Project
9 | Demand and supply analysis
10 | Financial Plan and mode of financing
11 | Project benefits and analysis
i. | Financial
ii. | Social benefits with indicators
iii. | Employment generation (direct and indirect)
iv. | Environmental impact
v. | Impact of delays on project cost and viability

## Slide 22
12 | Implementation schedule
13 | Management structure and manpower requirements including Specialized skills during execution and operational phases
14 | Additional projects/decisions required to maximize socio-economic benefits from the proposed project
15 | Certified that the project proposal has been prepared on the basis of instructions provided by the Planning Commission for the preparation of PC-I for Social Sector projects.