## Slide 1: The Project Team
Notes: <number>

## Slide 2: The (Dedicated) Project Team
The (dedicated) Project Team lies at one extreme end of the continuum which starts from undertaking projects using the (pure) functional form of project organization.
A project manager is selected to head a core group of personell assigned from two or more functional units of the organization and who are all required to work full-time on the project in question.
Project Teams are usually „cross-functional“ in nature and are a powerful means of dealing with complex assignments which may be difficult to do using other project organiza-tion forms.
Notes: <number>

## Slide 3: Forming a (Dedicated) Project Team
Corporation X
Human
Resources
Marketing
Engineering
Procurement
Manufacturing
Finance &
Administration
Project Manager
Project Team
MA1
MA2
MA3
EN1
EN2
EN3
MF1
MF2
MF3
PR1
PR2
Staff are assigned away from various departments to work full-time on the project.
Other Areas
Notes: <number>

## Slide 4: The Project Team - Advantages
No structural impact on the functional organization occurs – only the tempo-rary siphoning away of functional specialists from their respective areas for the duration of the project or for a phase of it when heir input is required in order to complete specialist tasks.
Notes: <number>

## Slide 5: The Project Team - Advantages
Project completion time is comparatively smaller due to project personell devoting their efforts to the project in question full-time and also because the flow of information and decision-making is generally not hindered by hierachies as it is in the functional form of organizing projects.
Notes: <number>

## Slide 6: The Project Team - Advantages
Motivation, feeling of iden-tification and cohesiveness are strong in the project.
Project personell share a common goal and they also share a collective responsibility for ensuring the realization of this goal.
Notes: <number>

## Slide 7: The Project Team - Advantages
Cross-functional cooperation is strongly encouraged and promoted as a means of achieving the project goal.
Cross-functional teams create a synergy effect which can handle tasks characterised by a high degree of complexity.
Notes: <number>

## Slide 8: The Project Team - Disadvantages
A major criticism of the (dedicated) project team relates to the cost factor.
Normally, a larger expense is involved because resources and facilities are assigned to the project on a full-time basis. Across projects, this may result in a duplication of infrastructure and work.
Notes: <number>

## Slide 9: The Project Team - Disadvantages
Projectitis – project personell evolve a collective identity encapsulating themselves from the enterprise, giving rise to a non-constructive „us“and „them“outlook. Sometimes this not only undermines the integration of the project effort back into mainstream operations but also the subsequent assimilation of project personell back into their respective functional areas.
Notes: <number>

## Slide 10: The Project Team - Disadvantages
The project may become over-dependent on the gamut of skills, expertise and experience held by the project personell and may not seek to incorporate fresh skills, expertise and experience which is held by individuals and organiza-tional entities which are outside the project.
Notes: <number>

## Slide 11: The Project Team - Disadvantages
The assimilation of project personell back into their respective functional units may prove difficult due to their prolonged absence from their units and the challenge of keeping up with the developments which have taken place in the functional units during the project period.
Notes: <number>

## Slide 12: Project Organization Forms and Project Performance Findings Based on Empirical Research
Notes: <number>

## Slide 13
The project‘s size
The project‘s strategic importance
The project‘s innovation requirement
The project‘s level of required integration across functional delineations
The project environment‘s complexity
The project budget and time constraints
The project resource requirement level of stability
In general – the higher the level of these factors, the greater is the requirement of autonomy and authority for the project manager and his/her team in order to ensure the success of the project (i.e. a strong project matrix or dedicated project team is desirable).
Determining The Best Project Organization Form
Notes: <number>

## Slide 14: Empirical Findings: Effectiveness of Project Organization Forms
Empirical research suggests that the „Project Matrix“ and „Project-Based Organization“ modes are the
most effective means of undertaking projects
Functional
Organization
Functional
Matrix
Balanced
Matrix
Project
Matrix
Project
Organizaton
Very
Ineffective
Ineffective
Effective
Very
Effective
Construction
New Product
Clifford F. Gray / Erik W. Larson, Project Management: The Managerial Process, 2. ed., 2003, p. 71
Notes: <number>

## Slide 15: Case Study: Product Development Projects
Erik W. Larson & David H. Gobeli examined the performance of different organizational structures with regard to the schedule, cost and technical performance of 540 development projects in 1987-88. The industries represented in the survey were pharmaceuticals, aero-space, computer and data processing products, telecommunications, medical instruments, glass products, petrochemical products, software development and household goods.
Notes: <number>

## Slide 16: Project Performance and Organizational Form (Meeting Schedule)
Notes: <number>

## Slide 17: Project Performance and Organizational Form (Controlling Cost)
Notes: <number>

## Slide 18: Project Performance and Organizational Form (Technical Performance)
Notes: <number>

## Slide 19: Project Performance and Organizational Form (Project Success Versus Complexity and Structure)
Notes: <number>

## Slide 20: Something to Keep in Mind
An organization can be expected to apply different forms of organization for its projects contained in its portfolio, using the criteria which were considered in the previous slide.
Pure Functional Form
Matrix Form
(Dedicated) Project Teams
Notes: <number>

## Slide 21: The Culture of an Organization and its Implications for Projects
Notes: <number>

## Slide 22: What is Organizational Culture?
Every organization has its own distinctive cul-ture which sets it apart from all other organi-zations, including those which are operating in the same field.
Organizational culture basically refers to a sys-tem of shared norms, beliefs, values, assump-tions, attitudes and behaviours which bind the members of the organization together and determine ‚how we do things around here‘.
Notes: <number>

## Slide 23: Relevance of Organizational Culture
Project managers must contend with several, often diverse cultures and subcultures existing within the diverse organizational spheres of their organizations (e.g. senior management, functional areas, PMO), and outside it (e.g. clients, contractors, suppliers, government agencies and other stakeholders).
A good ‚cultural management strategy‘ can be crucial for successfully managing a project.
Notes: <number>

## Slide 24: Organizational Culture – A Note of Caution!
Several research studies have been conducted over the years in the US and other countries to determine the relationship between Organiza-tional Culture and Organizational Performance.
Excercize caution in interpreting the results of these researches because studies undertaken in one country reflect the cultural, social and psychological context of that country and may not be valid for countries like Pakistan.
Notes: <number>

## Slide 25: Cultural Dimensions of Projects
Project
X
Functional Units
Other External Stakeholders
Project Customers
Ext. Project Input Suppliers
Organization as a Whole
Notes: <number>

## Slide 26: Interest in Organizational Culture
Inadequate management of ‚cultural conside-rations‘ may cause difficulties for projects. Therefore, it is essential to include the cultural component as an integral and important part of managing the overall project.
The culture of an organization determines the infrastructure and processes which it sets up and the support and encouragement which it gives to support projects.
Notes: <number>

## Slide 27: Organizational Culture and Projects
Organizational Culture
Project Performance
Supportive
(+)
Obstructive
(-)
Project performance is defined in terms of goal achievement within schedule and budget according to all given requirements and to the satisfaction of all key stakeholders
Organizational culture is defined in terms of the existing policies, infrastructure, metho-dology, processes, tools and all forms of support provided by the organization for its projects
Notes: <number>

## Slide 28: Measuring Organizational Culture
Gray and Larson have proposed ten cultural factors that are
related to project success:
Member Identity
Team Emphasis
People Focus
Unit Integration
Control
Risk Tolerance
Reward Criteria
Conflict Tolerance
Means-Ends-Orientation
Open-System Focus
Notes: <number>

## Slide 29: Drivers of a “Good Organizational Culture”
Without the visible, strong, active and sustained support and com-mitment of top management, it is not possible to create an organi-zational culture which facilitates projects. Top management must ensure that the projects being un-dertaken are aligned with the mis-sion, goals and objectives of the organization, that the value of pro-jects is acknowledged throughout the organization and that it is pre-pared to provide all forms of sup-port which projects need in order to be successfully undertaken.
Notes: <number>

## Slide 30: Drivers of a “Good Organizational Culture”
Projects need a strong infrastruc-ture support base if they are to have a high chance of succeeding. Many organizations have set up Project Management Offices which perform a host of specific support-ing functions in connection with projects. Organizations may have policies which require the applica-tion of sophisticated methodolo-gies (such as the PMBOK) on their projects, are following best practi-ces, and have devised ways to minimize friction between internal project stakeholders.
Notes: <number>

## Slide 31: Drivers of a “Good Organizational Culture”
To undertake projects successfully, an organization must equip its human resources with the requi-site knowledge and competencies and fully utilize their experience accumulated through their involve-ment in projects. Organizations with a good (project management) culture invest substantially in training programmes for their pro-ject managers and team members, offer handsome incentives, re-wards and promotional opportuni-ties for good performance, and accord due status.
Notes: <number>

## Slide 32: Drivers of a “Good Organizational Culture”
All projects are built on the foun-dations of communication, coope-ration and coordination between their stakeholders. Hence, it is imperative that the culture of the organization supports these activi-ties to the maximum possible ex-tent.
In organizations with a good (project management) culture, silo mentality is strongly discouraged and (formal and informal) commu-nication, cooperation and coordi-nation across functional lines is endorsed.
Notes: <number>

## Slide 33: The Project Management Office
Notes: <number>

## Slide 34: The Project Management Office
Many organizations of all sizes across the globe have established „Project Manage-ment Offices (PMOs)“ to serve as an organizational focal point for the effective and efficient management of their pro-grammes and projects. PMOs can perform many important functions and, if con-ceived and managed properly, are a huge asset for project-driven organizations.
Notes: <number>

## Slide 35: Internal Project Management Supporting Institutions in Pakistan
Several public and private-sector organizations which are operating in Pakistan, as well as the federal and provincial governments, have established structures (Project Management Units, Project Monitoring Units) performing PMO functions to support projects which they are undertaking.
Notes: <number>

## Slide 36: Some Typical Functions of a “Mature” PMO
Alignment of Projects with Organization’s Mission, Goals, Objectives
Project Portfolio Management
Resource Planning and Management
Generating Awareness in Organization of Project Management
Standardization of Policies, Processes, Protocolls and Documentaion
Recruitment and Selection of Project Managers and Team Members
Training in Project Management and Related Competencies, Skills
Monitoring, Evaluation and Auditing of Projects
Maintaining a Project Management Information System
Conseling and Mentoring of Project Staff
Benchmarking Best Practices
Archiving Documentation on Completed Projects
Refining Project Management Methodologies
Software Tools
Notes: <number>

## Slide 37: Project Management Offices: Survey Findings
Dr. Brian Hobbs from the Department of Management and Technology at the School of Management Sciences at the University of Quebec, Canada, has undertaken an insightful empirical research on PMOs entitled The Multi-Project PMO: A Global Analysis of the Current State of Practice.
Click on image to download the study (pdf-documnt).
Notes: <number>

## Slide 38: Literature on the Project Management Office
Click on images above to see details about the books at amazon.com
Notes: <number>