## Slide 1: Project Proposal Writing
M. Tahir Nadeem
Department of Education

## Slide 2: Concept
A project proposal is a detailed description of a series of activities aimed at solving a certain problem. A proposal should contain a detailed explanation of the:
Justification of a project;
Activities and implementation timeline;
Methodology; and
Human, material and financial resources required.

## Slide 3: Before Writing a Proposal
Interview past & prospective beneficiaries
Review past project proposals
Review past project evaluation reports
Organize focus groups
Check statistical data
Consult experts
Conduct small scale surveys
Hold community meetings

## Slide 4: Project basis (SWOT Analysis)

## Slide 5: Subject of SWOT analysis
Strengths
Advantages
Resources, Assets,
People, Experience,
infrastructure
--------------------------------
Opportunities
In-kind resources
Changes in society
Changes in policies
New technology
Weaknesses
Gaps in capabilities, Lack of competitive strength, Reputation, Finances, Reliability of data, Morale,
-------------------------------------
Threats
Political effects
Legislative effects
Environmental effects Market demands
Assumptions

## Slide 6: Justification of the Project
Benefits
Need
Output
Solutions
Importance
Impact

## Slide 7: Identifying the goal, objectives, and target group
Background of the project
Defined goal and objectives
The societal vision of the organization Expected short-term and long-term results Beneficiaries of the project
Problems solved by the project
ACTIVITY:
(Draw Objectives)

## Slide 8: Activity…..
AV Aids Material Development Workshop
Monthly tests in secondary school
Maintenance of college garden
Sports week at University level
Science exhibition at college level
Teacher training at school level

## Slide 9: Content of the project
Theme and main issues to be covered
Methods chosen to realize the goal and objectives
Activities to be implemented
Further needs to continue the project
ACTIVITY: Write down the contents of the above project

## Slide 10: Project location's and time schedule of activities
Location of different activities
Duration of the project
Starting and ending dates of the project
Schedule for individual activities
Summarized timeline of the project
ACTIVITY: Write down the time schedule of the above project

## Slide 11: Resources
Human resources
Financial resources
Infrastructure
ACTIVITY: Calculate the resources required for the above project

## Slide 12: Cost income sources
Total budget of the project
Detailed budget by activities and cost types
Rate and form of own contribution
Potential funders and sources of income
ACTIVITY: make a budget

## Slide 13: Description of the implementing organization and partners
Description of the implementing organization
Analysis of capacity and capability
Description of cooperative partners
Analysis of partners capacity and capability
ACTIVITY: give details of management staff

## Slide 14: Project team And management
The project coordinator
Communication method of the project team
Communication strategy and practice with the external environment

## Slide 15: Monitoring, Evaluation and follow-up
Success criteria of the project
Method and timing of monitoring and evaluation
Further plans and follow up
ACTIVITY: Identify performance indicators

## Slide 16: Preparing an Activity Plan
Activity Breakup into Tasks
Clarify sequence & dependence
Timeline for each task
Using milestones
Define expertise
Allocate tasks among the team

## Slide 17: Gantt Chart
Activities | 1st Week /Responsibility/ Space | 2nd Week /Responsibility/ Space | 3rd Week /Responsibility/ Space | 4th Week /Responsibility/ Space

## Slide 18
Thanks