## Slide 1: Project management
Organizing, planning and scheduling software projects

## Slide 2: Objectives
To introduce software project management and to describe its distinctive characteristics.
To discuss project planning and the planning process.
To show how graphical schedule representations are used by project management.

## Slide 3: Topics covered
Management activities
Project planning
Activity organization
Project scheduling

## Slide 4: Software project management
Concerned with activities involved in ensuring that software is delivered:
  on time
  on schedule
  in accordance with the requirements of the organizations developing and procuring the software

## Slide 5: Why is management important?
Software engineering is an economic activity and therefore is subject to economic, non-technical constraints.
Well-managed projects sometimes fail. Badly managed projects inevitably fail.
The objective of this lecture is to introduce management activities rather than teach you to be managers.
You can only learn to manage by managing

## Slide 6: Software management distinctions
The product is intangible.
The product is uniquely flexible.
The software development process is not standardized.
Most software projects are “one-off” projects.

## Slide 7: Management activities
Proposal writing
Project costing
Project planning and scheduling
Project monitoring and reviews
Personnel selection and evaluation
Report writing and presentations

## Slide 8: Management commonalities
These activities are not peculiar to software management.
Many techniques of engineering project management are equally applicable to software project management.
Technically complex engineering systems tend to suffer from the same problems as software systems.

## Slide 9: Project staffing
May not be possible to appoint the ideal people to work on a project:
  Project budget may not allow for the use of highly-paid staff.
  Staff with the appropriate experience may not be available.
  An organization may wish to develop employee skills on a software project.

## Slide 10: Project planning
Probably the most time-consuming project management activity.
Continuous activity from initial concept through to system delivery.
Plans must be regularly revised as new information becomes available.

## Slide 11: Project plan structure
Introduction
Project organization
Risk analysis
Hardware and software resource requirements
Work breakdown (User Stories)
Project schedule (Release & Iteration Planning)
Monitoring and reporting mechanisms

## Slide 12: Activity organization
Activities in a project should be organized to produce tangible outputs for management to judge progress.
Milestones are the end-point of a process activity.
Deliverables are project results delivered to customers.
Example: The waterfall process allows for the straightforward definition of progress milestones.

## Slide 13: Milestones and deliverables

## Slide 14: Project scheduling
Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Dependent on project managers intuition and experience.

## Slide 15: Scheduling problems
Estimating the difficulty of problems and hence the cost of developing a solution is hard.
Productivity is not proportional to the number of people working on a task.
Adding people to a late project makes it later because of communication overheads.
The unexpected always happens. Always allow contingency in planning.

## Slide 16: Bar charts and activity networks
Graphical notations used to illustrate the project schedule.
Show project breakdown into tasks. Tasks should not be too small. They should take about a week or two.
Activity charts show task dependencies and the the critical path.
Bar charts show schedule against calendar time.

## Slide 17: Task durations and dependencies

## Slide 18: Activity network

## Slide 19: Activity time-line

## Slide 20: Staff allocation

## Slide 21: Key points
Good project management is essential for project success.
The intangible nature of software causes problems for management.
Managers have diverse roles but their most significant activities are planning, estimating and scheduling.
Planning and estimating are iterative processes which continue throughout the course of a project.

## Slide 22: Key points
A project milestone is a predictable state where some formal report of progress is presented to management.
Activity charts and bar charts are graphical representations of a project schedule.