## Slide 1
Green Bank Project Management
What, Why, How, When, Who
Tuesday, 22nd July, 2003
John Ford and Richard Prestage
Notes: <number>

## Slide 2: Agenda
What is a Project?
What is Project Management?
Why do we need to do this?
How do we intend to do this?
When do we start?
Notes: <number>

## Slide 3: What is a project?
A Project is a temporary endeavor undertaken to create a unique product or service.
  Temporary
  Unique

## Slide 4: Project characteristics
Endeavors of any size may be a project
  Large and small projects demand different handling
Temporary
  Distinguishes projects from operations
Unique
  Not the same old thing

## Slide 5: What is not a project?
Emergency response to operations problems
  Callouts
  Repairs and troubleshooting
Routine operations support
  Maintenance of equipment
  Minor modifications and tuning of equipment

## Slide 6: What is project management
The management of projects (Well, Duh!)
A more academic, if not more useful, definition:
  The application of knowledge, tools, skill, and techniques to project activities in order to meet project requirements

## Slide 7: Project Management responsibilities
Manage the work involved in a project in terms of:
  Competing demands for scope, time, cost, risk, and quality
  Stakeholders with different needs and expectations
  Identified requirements

## Slide 8: Why do we need to do this?
Budgeting
Staff allocation
Schedule development
Schedule credibility
Sanity retention
Reporting what we are doing to the NRAO management as well as the NSF.

## Slide 9: How will we do this?
Project Management Organization
Project Planning
Project Communication

## Slide 10: Possible Organizations
Functional Organization
  Personnel organized by FUNCTION, i.e. electronics, software, operations, etc.

## Slide 11: Possible Organizations, continued
Project Organization
  Personnel organized by Projects, i.e. Ka Band receiver, Spectrometer, etc.

## Slide 12: Possible Organizations, continued
Matrix Organization
  Personnel organized in BOTH ways

## Slide 13: Matrix Management
Each staff member is a member of 2 distinct organizations
  Functional – Electronics, SDD, etc.
  Project – PTCS, Ka Band Receiver, etc.
Different types of Matrix organizations
  Strong Matrix
  Weak Matrix
  Balanced Matrix

## Slide 14: Our Organization
Our organization leans toward the balanced matrix organization
  Project Managers typically work directly for a functional manager
  Project Managers are part time managers
  Project Managers have limited authority
BUT: We also have a bit of the strong matrix organization.
  We have the Project Planning Committee, which serves as the manager of project managers.
  Project Managers have spending authority and budget responsibility

## Slide 15: Execution of Individual Projects
Each project is executed by a Project Team. For medium and large projects, Project Manager, Project Scientist and Project Engineer roles will be defined (may be combined into one or two individuals).
  Project Manager: The Project Manager is ultimately responsible for the overall success of the project. Manages the project budget and staffing allocations, sets the project schedule. Responsible for arranging project reviews, providing status reports, and so on. Represents the project to the GBT Project Planning Committee.
  Project Scientist: Responsible for setting the scientific requirements of the project, and ensuring that they are met.
  Project Engineer: Responsible for the technical aspects of the project.
Project Scientist and Engineer assist the Project Manager in the execution of the project e.g. preparation for design reviews, and so on.
Large projects might also define team leads for work packages

## Slide 16: Execution of Projects (continued)
Additional scientific and technical staff will be added to the project team as necessary.
The general level of effort will be agreed by the Project Planning Committee, and then the detailed staffing assignments will be agreed between the Project Manager and the appropriate functional Division Heads.
We will aim for continuity of effort levels and of specific individuals assigned to a project throughout its life, and specifically through each development cycle.
These may be reviewed and adjusted on a development-cycle to development cycle basis.

## Slide 17: Example Project – PTCS
Project Manager – Richard Prestage
Project Engineer – Kim Constantikes
Project Scientist – Jim Condon (Charlottesville)
Approximately eight ftes effort spread across all GB and CV scientific services divisions!
Work packages:
  Antenna Instrumentation (Team Lead: Kim)
  Engineering Measurement System (Team Lead: Kim)
  Astronomical Characterization (Team Lead: Richard)
  etc

## Slide 18: Project Reviews
Medium and Large projects expected to go through formal design reviews (might have caught some problems on earlier work!)
Depending upon scope, may require some or all of the following:
  Conceptual Design Review
  Preliminary Design Review
  Critical Design Review
  Final Lab Review
  Commissioning Review
(For more details, see wiki)

## Slide 19
Green Bank
Project Planning

## Slide 20: Project Planning Overview
An iterative process
User’s and Visiting Committee input gathered for strategic direction
NRAO Program Plan defines projects to be worked on during a year
The program plan for Green Bank is executed by the Green Bank Staff.
Simple, eh?

## Slide 21
Not Really!

## Slide 22: Green Bank Project Planning
Project Planning Committee oversees the program plan implementation
Major reviews are held every 6 months
Mid-term reviews held every quarter
Work is planned out over 6 week cycles by project managers, with specific development deliverables each cycle.
Program Planning Committee resolves short-term conflicts over resources on a weekly basis.

## Slide 23: Project Planning Committee:
R. Anderson, C. Bignell, D. Egan, J. Ford, P. Jewell, R. Maddalena, R. Prestage, N. Radziwill
Meets weekly to resolve short-term conflicts, look ahead to the rest of the 6 week development cycle
Meets each 6 weeks with all interested personnel in planning the next 6 week development cycle
Meets quarterly to review progress on 6 month goals, perform mid-course corrections

## Slide 24: Project Initiation
Step 1 – Project Proposal submitted
  By anyone
  Submit to a member of the project planning committee
  Format:
    1 page or less written summary.
      email, fax, napkin, etc. O.K.
    Should include:
      scope, strategic value, possible work packages, time frame
  IDEAS OF ANY SORT CAN BE SUBMITTED WITH ANY AMOUNT OF THE ABOVE DOCUMENTATION, AND WILL BE CONSIDERED

## Slide 25: Project Initiation
Step 2 – Project Charter
Developed by the originator of the project
Covers:
  Why the project is important, including compelling information on items such as timeliness.
  Scope of the project
  Preliminary scientific justification
  Outline of the potential solution
  Proposed project team
  Background information that the project team will need to know to execute the project

## Slide 26: Project Initiation
Step 3 – Formal Proposal
Required for large projects (Months or years of effort)
  Beyond the scope of this meeting!

## Slide 27: Project Initiation
All of our staff is fully committed right now
We don’t anticipate starting any new significant projects any time soon

## Slide 28: Project communication
Absolutely critical to the success of our projects!
Project Meetings
Planning Meetings
Weekly Coordination Meetings
Internet Collaboration Tool: wiki.gb.nrao.edu
GBT Development Plan

## Slide 29: Project meetings
Project team members
Short, informational meetings

## Slide 30: Weekly coordination meetings
Attended by the Project Planning Committee
Approves activities for the next 2 weeks on the GBT resource calendar
Discusses GBT science, test. and commissioning scheduling
Discusses other problems of cross-division importance
Discusses observer comments received during the previous week

## Slide 31: 6 week cycle planning meetings
Plan the work to be done on all projects in all disciplines for the next 6 weeks
Attended by:
  Project Planning Committee
  Project Engineers
  Project Managers
  Project Scientists
  Division Heads
  Any others with an interest

## Slide 32: Quarterly reviews
Review progress against milestones for each project
Set milestones for next quarter
Reports on each project submitted by Project Managers prior to the meeting
Attended by:
  Project Planning Committee
  Project Managers
Outcome of this meeting becomes the contents of the Quarterly Report

## Slide 33: Internet Collaboration Tool
Wiki.gb.nrao.edu

## Slide 34: Wiki Description
The GB Collaboration Web, built on TWiki, is a flexible, powerful, secure, yet simple web-based collaboration platform. This site can be used to run a project development space, a document management system, a knowledge base or any other groupware tool either on an intranet or on the Internet.
See http://twiki.org/ For more gory details

## Slide 35: Project Planning wiki
GB.Planning
Contains documents describing the projects underway, their milestones, and the plans for the current 6 weeks and quarter.
Can be edited by any of the project managers or project planning committee members
Can (soon!) produce nice hardcopies of the documents easily
Maintains history, so that older versions can be retrieved
We should maintain a wiki for each project, at some point.

## Slide 36: I Can’t Wait! When can we start?
Now!
1st 6 week planning meeting August 4th
1st Quarterly Review meeting mid-September

## Slide 37: Review
Projects are Temporary arrangements of effort and money to accomplish a goal
Project Management is effort expended to ensure the success of a project
In a Matrix organization, people are members of 2 groups. For matters relating to a project, they take direction from the project manager.
We are developing a more advanced planning and tracking process

## Slide 38
Our aim is to become more systematic in our planning -
more effective, not more bureaucratic

## Slide 39: Strong Matrix Organization

## Slide 40: Weak Matrix Organization

## Slide 41: Balanced Matrix Organization
Notes: <number>
Project managers have medium amount of authority.

## Slide 42: Strong vs. Balanced Matrix