## Slide 1: How to estimate a cost of a Project?
Hira Saeed

## Slide 2: What is Cost and Project Cost Management?
Cost is a resource sacrificed or foregone to achieve a specific objective, or something given up in exchange.
Costs are usually measured in monetary units, such as dollars.
Project cost management includes the processes required to ensure that the project is completed within an approved budget.

## Slide 3: Project Cost Management Processes
Cost estimating: Developing an approximation or estimate of the costs of the resources needed to complete a project.
Cost budgeting: Allocating the overall cost estimate to individual work items to establish a baseline for measuring performance.
Cost control: Controlling changes to the project budget.

## Slide 4: Estimating Projects
Estimating
  The process of forecasting or approximating the time and cost of completing project deliverables.
  The task of balancing expectations of stakeholders and need for control while the project is implemented.
Types of Estimates
  Top-down (macro) estimates: analogy, group consensus, or mathematical relationships
  Bottom-up (micro) estimates: estimates of elements of the work breakdown structure

## Slide 5: Why Estimating Time and Cost Are Important
To support good decisions.
To schedule work.
To determine how long the project should take and its cost.
To determine whether the project is worth doing.
To develop cash flow needs.
To determine how well the project is progressing.
To develop time-phased budgets and establish the project baseline.

## Slide 6: Factors Influencing the Quality of Estimates
Quality of Estimates
Project Duration
People
Project Structure and Organization
Padding Estimates
Organization Culture
Other (Non project) Factors
Planning Horizon

## Slide 7: Estimating Guidelines for Times, Costs, and Resources
Have people familiar with the tasks make the estimate.
Use several people to make estimates.
Base estimates on normal conditions, efficient methods, and a normal level of resources.
Use consistent time units in estimating task times.
Treat each task as independent, don’t aggregate.
Don’t make allowances for contingencies.
Adding a risk assessment helps avoid surprises to stakeholders.

## Slide 8: Estimating Projects: Preferred Approach
Make rough top-down estimates.
Develop the WBS.
Make bottom-up estimates.
Develop schedules and budgets.
Reconcile differences between top-down and bottom-up estimates

## Slide 9: Apportion Method of Allocating Project Costs Using the Work Breakdown Structure

## Slide 10: Types of Costs
Direct Costs
  Costs that are clearly chargeable to a specific work package.
    Labor, materials, equipment, and other
Direct (Project) Overhead Costs
  Costs incurred that are directly tied to an identifiable project deliverable or work package.
    Salary, rents, supplies, specialized machinery
General and Administrative Overhead Costs
  Organization costs indirectly linked to a specific package that are apportioned to the project

## Slide 11: Refining Estimates
Reasons for Adjusting Estimates
  Interaction costs are hidden in estimates.
  Normal conditions do not apply.
  Things go wrong on projects.
  Changes in project scope and plans.
Adjusting Estimates
  Time and cost estimates of specific activities are adjusted as the risks, resources, and situation particulars become more clearly defined.

## Slide 12: Typical Problems with Cost Estimates
Developing an estimate for a large software project is a complex task that requires a significant amount of effort.
People who develop estimates often do not have much experience.
Human beings are biased toward underestimation.
Management might ask for an estimate, but really desire a bid to win a major contract or get internal funding.

## Slide 13: Types of Budgeting
Top-down
Bottom-up

## Slide 14: Top-Down Budgeting
The technique of developing a budget by comparing this project to past ones using the judgment and experience of management.
Typically an overall budget is assigned to the project to be distributed to the individual tasks.
If the projects being used for comparison are similar enough, this process can result in a fairly accurate total number.
The process of distributing the total can create a lot of conflict among the management team.

## Slide 15: Bottom-Up Budgeting
The process of developing budgets by asking the people who will perform the individual tasks on the WBS for their estimates.
These individual numbers are then rolled up to a summary for presentation to management.