## Slide 1: Process Assurance
Lecture # 38

## Slide 2: Today’s Lecture
In our discussions on software quality assurance, we have divided the quality assurance into two major aspects
  Process-related
  Product-related
Today, we’re going to talk about process-related issues of software quality and discuss process assurance

## Slide 3: Process Assurance

## Slide 4: Process Assurance - 0
Process assurance makes certain that the process for building and delivering software is robust and allows for the delivery and maintenance of the products

## Slide 5: Process Assurance - 1
Process assurance consists of the collective activities carried out while developing a product to ensure that the methods and techniques used are integrated, consistent, and correctly applied
Emphasis is given to cost, time, technical requirements, testing measurements, and prototyping

## Slide 6: Process Assurance - 2
Process assurance involves the interrelationships of several different components. Depending on how these are managed, they can have a major positive impact on the products
Once an effective process assurance program is put in place and shown to be beneficial, then emphasis can be placed in making verification and validation strategies effective and in improving the quality of the products

## Slide 7: Process Assurance - 3
Successful process assurance is based on planning and organization
There are several important aspects of planning and organization that must be considered before starting the project
I’ll show you a picture, which captures the components of planning and organization

## Slide 8: Components of Planning and Organization
Planning & Organization
Project
Team
Project
Standards
Schedule
Monitoring
Project
Risks
Steering
Committee
Effective
Communication
Integrated
Technology
Measurement
Project
Tracking
Estimating

## Slide 9: Project Team
Project team is the project manager’s only means of reaching the project goals
Formation of project team is vital to success
Size of the team depends on the size and complexity of the project
Right mix of technical knowledge and experience
Fostering of mutual respect within team and maintains good morals

## Slide 10: Project Standards - 1
Before the project is started, standards should be established for activities like requirements gathering, design development, and unit testing
Standards should also be developed for quality control activities, like walkthroughs, reviews, and inspections

## Slide 11: Project Standards - 2
Many companies follow IEEE software engineering standards or they have their internally developed standards
Standards should be flexible enough to be applied to large or small projects
Any deviations from the standards should be approved by the project team and the reason for such deviation should be noted in the minutes of the project meetings

## Slide 12: Schedule Monitoring - 1
Stringent deadlines for the project are frequently established by management, end users, a project sponsor, or a client with no regard to the reality of achievement
The project manager is then designated to meet unrealistic expectations of the project completion date
For this reason, the project start date, milestones, and completion date should be negotiated upfront

## Slide 13: Schedule Monitoring - 2
If the unrealistic date is accepted and the project activities are then made to fit within this time frame, the quality of the project certainly will suffer
The key to an “on-time” project lies in the ability to identify the critical path before starting the project

## Slide 14: Schedule Monitoring - 3
The critical path of a project is where problems that may affect the overall schedule are faced
Develop systematic work breakdown structures which identify task groupings (tasks that can be combined together), task sequences, and entrance/exit criteria for each task

## Slide 15: Schedule Monitoring - 4
To define tasks, follow the guidelines of the system development methodology used by your organization
In the absence of a development methodology, obtain copies of task lists and task dependencies from other projects and customize them to suit your needs of the current project

## Slide 16: Schedule Monitoring - 5
Clearly defined work breakdown structures will assist in selecting the correct skilled resources
At the same time, using the breakdown structures also ensures that no activity is forgotten
The technique of breaking down activities into smaller tasks takes an impossibly complex project and reorganizes it into manageable pieces under the direction of the project manager

## Slide 17: Schedule Monitoring - 6
Once you have defined the critical path, review the tasks and schedule with the project team members and other significantly impacted individuals

## Slide 18: Schedule Monitoring - 7
Since these people are the stakeholders and are affected by the project in one or more of the following ways:
  Their budget is charged for all or part of the project
  The department’s resources are used by the project
  The department has either existing projects or ongoing projects that are affected by the new project

## Slide 19: Schedule Monitoring - 8
Avoid the most common mistake of adding another resource to shorten or meet the schedule

## Slide 20: Project Tracking
Project tracking is an important activity in project management
Project tracking tools should be used to monitor the progress of project schedule, and estimate resources

## Slide 21: Estimation
Realistic estimates allow you to discuss alternative approaches at the start of the project
Estimates are not foolproof
Allow time for resource management and unforeseen events, like the illness of a team member
Revise estimates, and update plans

## Slide 22: Effective Communication
Effective communication between the management and project team is a critical interpersonal skill
  Listening
  Observing
  Giving guidance
Delegation of responsibility
Informal negotiation

## Slide 23: Steering Committee - 1
A committee responsible for defining project policy, reviewing the project milestones, and evaluating risk factors must be established
Members of the committee should represent all the impacted areas of the business. They should be knowledgeable enough to make informed technological decisions and be able to change the course if needed

## Slide 24: Steering Committee - 2
It is responsible for
  Estimating the time that will be required to maintain the system
  Deciding on the type of support required from the operations for the running of the system
  Deciding when the data will be available and how it will be managed, reported, and used
  Forming a configuration control board (CCB) that manages the impact of changes

## Slide 25: Project Risks - 1
Every project has risks associated with them, some more than others
There is need to identify and address the risk factors upfront
All risk factors should be discussed with the project team, management, and users
A risk mitigation policy needs to be developed

## Slide 26: Project Risks - 2
Project risks can be assessed in three categories
  Business risk
  Technology risk
  Project size risk

## Slide 27: Project Risks - 3
Risks can be minimized by
  Implementing controls from the initiation stage and by ensuring pre-established development standards are followed
  Providing project management training
  Reducing the scope of the project by incremental development or phased development

## Slide 28: Project Risks - 4
Technical risk is encountered when the project team utilizes a new technology like new hardware or new development methodology for the first time
Technical risks can be controlled by
  Appointing a qualified technical project leader
  Implementing a strong, independent quality control group to evaluate the progress of the project and project deliverable

## Slide 29: Project Risks - 5
  Getting additional technical expertise from outside consultants who have expertise and the knowledge to make a difference in the ultimate quality of the project

## Slide 30: Measurement - 1
Establishing measurement criteria, against which each phase of the project will be evaluated, is vital
When exit criteria is well defined, it is sufficient to evaluate the outcome of each phase against the exit criteria and move forward

## Slide 31: Measurement - 2
If the outcome of each phase does not meet the performance criteria, the project manager should be able to control the project by evaluating the problems, identifying the deviations, and implementing new processes to address the deviations

## Slide 32: Measurement - 3
The pre-established quality goals for the project can also serve as criteria against which the project can be measured

## Slide 33: Measurement - 4
Processes should be established to
  Enable the organization to address customer complaints
  Give the organization statistics regarding the types of customer calls
  Incorporate reporting and handling of customer problems
  Enable management to make staffing decisions based on the number of customer calls

## Slide 34: Integrated Technology - 1
Strategy for Integrated Technology should be considered by management in relation to the other business needs
This will empower the management to react to the operational needs of the business and, at the same time, take an inventory of the current status of various systems, projects, and the ability of technical staff to support any future projects

## Slide 35: Integrated Technology - 2
The IT trends, competitors, and demands of the customers should be visible to the management
Parts of the new system that will be interfacing with existing system should be identified so that the impact can be evaluated
If technology is new and not well understood, allowances to incorporate experiments should be made in the overall project plan and schedule

## Slide 36: Causes of Failure in Process Assurance
Lack of Management Support
Lack of User Involvement
Lack of Project Leadership
Lack of Measures of Success

## Slide 37: Symptoms of Process Failure - 1
Commitments consistently missed
  Late delivery
  Last minute crunches
  Spiraling costs
No management visibility into progress
  You’re always being surprised

## Slide 38: Symptoms of Process Failure - 2
Quality problems
  Too much rework
  Functions do not work correctly
  Customer complaints after delivery
Poor morale
  People frustrated
  Is anyone in charge?

## Slide 39: Common Misconceptions
I don’t need process, I have
  Really good people
  Advanced technology
  An experience manager
Process
  Interfaces with creativity
  Equals bureaucracy + regimentation
  Isn’t needed when building prototypes
  Is only useful on large projects
  Hinders agility in fast-moving markets
  Costs too much

## Slide 40
Everyone realizes the importance of having a motivated, quality work force but even our finest people cannot perform at their best when the process is not understood or operating at its best
Process, people, and technology are the major determinants of product cost, schedule, and cost

## Slide 41: Process, People, and Technology
People
Process
Technology

## Slide 42
The quality of a system is highly influenced by the quality of the process used to acquire, develop, and maintain it
While process is often described as a node of the process-people-technology triad, it can also be considered the “glue” that ties the triad together

## Slide 43: References
Inroads to Software Quality by Alka Jarvis and Vern Crandall (Chapter 1)
Software Quality: Analysis and Guidelines for Success by Capers Jones