Project Management					Sample question for Papers

Q. No. 1.

Answer the objective type part of the examination given to you.

Q. No. 2.

What is financial feasibility analysis? List its main components.

Q. No. 3.

The Sunny Computers Corporation is considering investing in developing new software. A corporate planning group has recommended the firm to go ahead with the test and development phase of new software. This preliminary phase will last one year and costs 900 million. Furthermore, the group believes that there is a 50% chance that test will prove to be successful. If the initial tests are successful, Sunny Computers can go ahead with full-scale production. This investment phase will cost $1500 million. Production will occur over the next 4 years. If the test is successful then every year there will be a cash inflow of $1488 million for next 4 years and in case of failure there will be a cash inflow of $375.9 million every year for next 4 years. Draw the decision tree and recommend that whether the company should conduct the test or not.

Q. No. 4.

Answer the objective type part of the examination given to you.

Q. No. 5.

Define project charter and also list it’s at least six main components.

Q. No. 6.

Define:  (a) Project management   (b) Float/Slack (c) Project activity (d) dependency

Q. No. 7.

A construction project is scheduled to be started and finished through the whole month of May, 2019, at $ 155,000. At the end of 17 days, the project is 35% complete and actual cost of the project is $ 80,000. Calculate it’s PV, EV, CV, SV, CPI, SPI and EAC and any savings or additional expenditures at the completion of project.